## Sp1
Sprint 1 Backlog

				Effort
		Days	Totals	4					#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	0		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.
	2		Planned	4
	1		Planned	6
	2		Planned	3
	3		Planned	2
	4		Planned	1
	3		Planned	3

## Product Backlog
id	User Stories	Priority	Story points ( 1-5)	Unknown Issues
1	Admin käyttäjä: Haluan lisätä ja poistaa käyttäjiä	1	2	Valmiina Spring erimerkki projektissa
2	Admin käyttäjä: Haluan säätää käyttäjien oikeuksia	1	2	Valmiina Spring esimerkki projektissa
3	Myyjä:Haluan tallentaa uusia asiakkaita.	1	2
4	Myyjä:Haluan tallentaa uusia asiakasyrityksiä.	1	2
5	Myyjä:Haluan liittää asiakkaat yrityksiin	2	1
6	Myyjä: Haluan tallentaa tiedot uudesta kaupasta	2	1
7	Sihteeri:Haluan hakea asiakkaita eri hakukriteereillä	3	1
8	Teknikko: Haluan luoda uuden toimituksen tiedoilla	2	1
9	Teknikko:Haluan liittää toimitukseen teknisen määrittelyn, joka koostuu N:stä dokumentista.	3	1
10	Laskuttaja: Haluan liittää toimitukseen laskun tiedoilla	3	1

			14

				Other Comments:

## Product Tasks
Product Tasks

Item ID	Item Description	Status	Sprint	Priority
1.1	Spring esimerkin integrointi Siriin – fi.siri.kayttaja			1	.
1.2	JPA:n lisäys erimerkkiluokkiin			0
1.3	JSP sivun muutos			1
1.4	Testaus			1
1.5	Siri logo	Done		1
1.6	Projektin pääsivu			1

2.1	Spring esimerkin integrointi Siriin			1
2.2	JPA:n lisäys erimerkkiluokkiin			1
2.3	Testaus			1

3.1	Asiakastaulu suunnittelu – fi.siri.asiakas	Done		1
3.2	Asiakas Entity			1
3.3	Asiakas DAO			1
3.4	Asiakas Kontolleri			1
3.5	JSP sivut			1
3.6	testaus			1

4.1	Yritystaulun suunnittelu – fi.siri.yritys			1
4.2	Yritys Entity			1
4.3	Yritys DAO			1
4.4	Yritys Kontrolleri			1
4.5	JSP sivut			1
4.6	testaus			1

## Sprint 1
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	5			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	105	98	98	98	98	98	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	21	Done days	5		105	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	5		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5
Spring esimerkin integrointi Siriin – fi.siri.kaytt	1.1	Jouni	Planned	15	15	15	15	15	15
JPA:n lisäys erimerkkiluokkiin	1.2	Jouni	Planned	3	3	3	3	3	3
JSP sivun muutos	1.3	Jouni	Planned	1	1	1	1	1	1
Testaus	1.4	Jouni	Planned	10	10	10	10	10	10
Siri logo	1.5	Kari	Done	1	0	0	0	0	0
Projektin pääsivu	1.6	Kari & Mika	Planned	7	7	7	7	7	7
Spring esimerkin integrointi Siriin	2.1	Jouni	Planned	3	3	3	3	3	3
JPA:n lisäys erimerkkiluokkiin	2.2	Jouni	Planned	1	1	1	1	1	1
Testaus	2.3	Jouni	Planned	10	10	10	10	10	10
				0	0	0	0	0	0
Asiakastaulu suunnittelu – fi.siri.asiakas	3.1	Seija	Done	1	0	0	0	0	0
Asiakas Entity	3.2	Seija	Planned	2	1	1	1	1	1
Asiakas DAO	3.3	Seija	Planned	3	2	2	2	2	2
Asiakas Kontolleri	3.4	Seija	Planned	6	5	5	5	5	5
JSP sivut	3.5	Seija		10	8	8	8	8	8
Testaus	3.6	Seija	Planned	10	10	10	10	10	10

Yritystaulu suunnittelu – fi.siri.yritys	4.1	Kari&Mika	Planned	10	10	10	10	10	10
Yritys Entity	4.2	Kari&Mika	Planned	4	4	4	4	4	4
Yritys DAO	4.3	Kari&Mika	Planned	4	4	4	4	4	4
Yritys Kontrolleri	4.4	Kari&Mika	Planned	4	4	4	4	4	4
JSP sivut	4.5	Kari&Mika	Planned	10	10	10	10	10	10
testaus	4.6	Kari&Mika	Planned	10	10	10	10	10	10
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0

## Sprint 2
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	5			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#REF!	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#REF!	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5

## Sprint 3
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	20			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#NAME?	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20

## Sprint 4
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	20			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#NAME?	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20

## Sprint 5
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	20			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#NAME?	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20

## RESOURCES
Resurssit sprintteihin
Henkilö	Sprint 1	Sprint 2
Kari	30	30
Jouni	35	35
Mika	35	35
Seija	35	35
SUMMA	135	135

Tiimin osaaminen
- tietokantaosaamista
- Java, JavaScript
- JUnit
- Mock-testaus
- HTML, CSS