## Sp1
Sprint 1 Backlog

				Effort
		Days	Totals	4					#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	0		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.
	2		Planned	4
	1		Planned	6
	2		Planned	3
	3		Planned	2
	4		Planned	1
	3		Planned	3

## Product Backlog
id	User Stories	Priority	Story points ( 1-5)	Unknown Issues
1	Admin käyttäjä: Haluan lisätä ja poistaa käyttäjiä	1	2	Valmiina Spring erimerkki projektissa
2	Admin käyttäjä: Haluan säätää käyttäjien oikeuksia	1	2	Valmiina Spring esimerkki projektissa
3	Myyjä:Haluan tallentaa uusia asiakkaita.	1	2
4	Myyjä:Haluan tallentaa uusia asiakasyrityksiä.	1	2
5	Myyjä:Haluan liittää asiakkaat yrityksiin	2	1
6	Myyjä: Haluan tallentaa tiedot uudesta kaupasta	2	1
7	Sihteeri:Haluan hakea asiakkaita eri hakukriteereillä	3	1
8	Teknikko: Haluan luoda uuden toimituksen tiedoilla	2	1
9	Teknikko:Haluan liittää toimitukseen teknisen määrittelyn, joka koostuu N:stä dokumentista.	3	1
10	Laskuttaja: Haluan liittää toimitukseen laskun tiedoilla	3	1

			14

				Other Comments:

## Product Tasks
Product Tasks

Item ID	Item Description	Status	Sprint	Priority
1.1	User entity	Done		1	.
1.2	UserController	Done		1
1.3	UserDAO	Done		1
1.4	JSP sivut	Done		1
1.5	Testaus	Done		1
1.6	Siri logo	Done		1
1.7	Projektin pääsivu	Done		1
1.8	Login	Done		1

2.1	UserRole	Done		1
2.2	UserRoleDAO	Done		1
2.3	Muutokset UserControlleriin	Done		1
2.4	JPA:n lisäys erimerkkiluokkiin	Done		1
2.5	Testaus	Done		1

3.1	Asiakastaulu suunnittelu – fi.siri.asiakas	Done		1
3.2	Asiakas Entity	Done		1
3.3	Asiakas DAO	Done		1
3.4	Asiakas Kontolleri	Done		1
3.5	JSP sivut	Done		1
3.6	testaus	Done		1

4.1	Yritystaulun suunnittelu – fi.siri.yritys	Done		1
4.2	Yritys Entity	Done		1
4.3	Yritys DAO	Done		1
4.4	Yritys Kontrolleri	Done		1
4.5	JSP sivut	Done		1
4.6	testaus	Done		1

5.1	Asiakas-taulu			1
5.2	Yritys-taulu			1
5.3	Asiakas DAO
5.4	Yritys DAO
5.5	AsiakasController			1
5.6	YritysController			1
5.7	JSP sivut			1
5.8	DAO luokkien Junit testit			1
5.9	Kontrollerien testit			1

## Sprint 1
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	5			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	99	89	88	88	55	40	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	24	Done days	5		99	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	5		1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5
User	1.1	Seija	Done	15	15	15	15	15	0
UserDAO	1.2	Seija	Done
UserController	1.3	Seija	Done	3	3	3	3	0	0
JSP sivut	1.3	Jouni	Done	1	1	1	1	1	1
Testaus	1.7	Seija	Done	10	10	10	10	10	10
Login	1.8	Jouni&Seija	Done	5	5	5	5	0	0
Käyttäjien lisäys ja poisto		Seija	Done	5	5	5	5	0	0
Siri logo	1.5	Kari	Done	1	1	0	0	0	0
Projektin pääsivu	1.6	Kari & Mika	Done	7	7	7	7	0	0
Spring esimerkin integrointi Siriin	2.1	Jouni	Planned	3	3	3	3	3	3
JPA:n lisäys erimerkkiluokkiin	2.2	Jouni	Planned	1	1	1	1	1	1
Testaus	2.3	Jouni	Planned	10	10	10	10	10	10
				0	0	0	0	0	0
Asiakastaulu suunnittelu – fi.siri.asiakas	3.1	Seija	Done	1	0	0	0	0	0
Asiakas Entity	3.2	Seija&Mika	Ongoing	2	1	1	1	1	1
Asiakas DAO	3.3	Seija&Mika	Ongoing	3	2	2	2	1	1
Asiakas Kontolleri	3.4	Seija&Mika	Ongoing	6	5	5	5	1	1
JSP sivut	3.5	Seija&Mika	Ongoing	10	8	8	8	1	1
Testaus	3.6	Seija	Planned	10	10	10	10	10	10

Yritystaulu suunnittelu – fi.siri.yritys	4.1	Kari&Mika	Done	1	0	0	0	0	0
Yritys Entity	4.2	Kari&Mika	Done	1	0	0	0	0	0
Yritys DAO	4.3	Kari&Mika	Done	2	0	0	0	0	0
Yritys Kontrolleri	4.4	Kari&Mika	Ongoing	2	2	2	2	1	1
JSP sivut	4.5	Kari&Mika	Ongoing	10	9	9	9	1	1
testaus	4.6	Kari&Mika	Planned	10	10	10	10	10	10
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0	0	0	0	0
				0	0

## Sprint 2
Sprint 2 Backlog		Work Remaining (h)

Sprint implementation days	5			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	0	3	2	2	2	8	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	21	Done days	5		0	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5
US 2					1
UserRole		Jouni	Done	0	0	0	0	0	0
UserRoleDAO		Jouni	Done	0	0	0	0	0	0
Muutokset UserControlleriin		Jouni	Done	0	0	0	0	0	0
Testaus		Seija, Mika	Done	0	0	0	0	0	0
Validointi		Kari	Done	0	0	0	0	0	0
Loggautuneen käyttäjän näyttäminen		Seija	Done	0
US 3				0	0	0	0	0	0
Asiakas Entity fix		Kari	Done	0	0	0	0	0	0
AsiakasDAO fix		Kari	Done	0	0	0	0	0	0
AsiakasKontolleri fix		Kari	Done	0	0	0	0	0	0
Validointi		Kari	Done	0	0	0	0	0	1
Valokuvan upload add ja edit		Seija	Done	0	0	0	0	0	2
JSP sivut fix		Kari	Done	0	0	0	0	0	3
Testaus		Seija, Mika	Done	0	2	2	2	2	2
US 4				0	0	0	0	0	0
Yritys Kontrolleri		Kari	Done	0	0	0	0	0	0
JSP sivut		Kari	Done	0	0	0	0	0	0
Testaus		Mika, Seija	Done	0	0	0	0	0	0
Validointi		Kari	Done	0	0	0	0	0	0
Kaikkien sivujen ulkoasu		Mika	Done	0

## Sprint 3
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	20			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#NAME?	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20

## Sprint 4
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	20			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#NAME?	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20

## Sprint 5
Sprint 1 Backlog		Work Remaining (h)

Sprint implementation days	20			Effort	Remaining on implementation day…
Trend calculated based on last	5	Days	Totals	#NAME?	#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Task rows	1	Done days	1		#NAME?	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
Warning! These are necessary		Trend			#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A	#N/A
template rows		Trend Days	Err:504		Err:504	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Task name	Story ID	Responsible	Status	Est.	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20

## RESOURCES
Resurssit sprintteihin
Henkilö	Sprint 1	Sprint 2
Kari	30	30
Jouni	35	35
Mika	35	35
Seija	35	35
SUMMA	135	135

Tiimin osaaminen
- tietokantaosaamista
- Java, JavaScript
- JUnit
- Mock-testaus
- HTML, CSS